## Index
Project Estimation and Timeline
Document ID | 1
Revision History
Ver. No. | Release Date | Comments | Released By
1 | 2025-07-10 | FA Glass Order Entry Effort Estimation | Suhail Ahmed

## Criteria
Estimation Criteria Setup
Platform | Phase | Description | Complexity (Simple / Complex / Average) | No of features in 4 groups [ 1 to 4 ]
|  |  |  | 0-5 | 6-10 | 11-15 | >15
|  |  |  | 1 | 2 | 3 | 4
Desktop | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Simple | 0.5
Desktop | UI Module | Custom Field Validations , Java scripting , Front end coding | Simple | 0.5
Desktop | BL | Business Logic & Validations | Simple | 1
Desktop | General |  | Simple | 0.5
Desktop | Service API |  | Simple | 1
Desktop | DB Structure |  | Simple | 0.5
Desktop | DB Programming |  | Simple | 0.5
Desktop | DB UDF |  | Simple | 0.5
Desktop | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Average
Desktop | UI Module | Custom Field Validations , Java scripting , Front end coding | Average
Desktop | BL | Business Logic & Validations | Average
Desktop | General |  | Average
Desktop | Service API |  | Average
Desktop | DB Structure |  | Average
Desktop | DB Programming |  | Average
Desktop | DB UDF |  | Average
Desktop | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Complex
Desktop | UI Module | Custom Field Validations , Java scripting , Front end coding | Complex
Desktop | BL | Business Logic & Validations | Complex
Desktop | General |  | Complex
Desktop | Service API |  | Complex
Desktop | DB Structure |  | Complex
Desktop | DB Programming |  | Complex
Desktop | DB UDF |  | Complex
Web | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Simple | 0.5
Web | UI Module | Custom Field Validations , Java scripting , Front end coding | Simple | 0.5
Web | BL | Business Logic & Validations | Simple | 1
Web | General |  | Simple | 0.5
Web | Service API |  | Simple | 1
Web | DB Structure |  | Simple | 0.5
Web | DB Programming |  | Simple | 0.5
Web | DB UDF |  | Simple | 0.5
Web | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Average
Web | UI Module | Custom Field Validations , Java scripting , Front end coding | Average
Web | BL | Business Logic & Validations | Average
Web | General |  | Average
Web | Service API |  | Average
Web | DB Structure |  | Average
Web | DB Programming |  | Average
Web | DB UDF |  | Average
Web | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Complex
Web | UI Module | Custom Field Validations , Java scripting , Front end coding | Complex
Web | BL | Business Logic & Validations | Complex
Web | General |  | Complex
Web | Service API |  | Complex
Web | DB Structure |  | Complex
Web | DB Programming |  | Complex
Web | DB UDF |  | Complex
Mobile | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Simple | 0.5
Mobile | UI Module | Custom Field Validations , Java scripting , Front end coding | Simple | 0.5
Mobile | BL | Business Logic & Validations | Simple | 1
Mobile | General |  | Simple | 0.5
Mobile | Service API |  | Simple | 1
Mobile | DB Structure |  | Simple | 0.5
Mobile | DB Programming |  | Simple | 0.5
Mobile | DB UDF |  | Simple | 0.5
Mobile | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Average
Mobile | UI Module | Custom Field Validations , Java scripting , Front end coding | Average
Mobile | BL | Business Logic & Validations | Average
Mobile | General |  | Average
Mobile | Service API |  | Average
Mobile | DB Structure |  | Average
Mobile | DB Programming |  | Average
Mobile | DB UDF |  | Average
Mobile | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Complex
Mobile | UI Module | Custom Field Validations , Java scripting , Front end coding | Complex
Mobile | BL | Business Logic & Validations | Complex
Mobile | General |  | Complex
Mobile | Service API |  | Complex
Mobile | DB Structure |  | Complex
Mobile | DB Programming |  | Complex
Mobile | DB UDF |  | Complex
Web | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Simple | 0.5
Web | UI Module | Custom Field Validations , Java scripting , Front end coding | Simple | 0.5
Web | BL | Business Logic & Validations | Simple | 1
Web | General |  | Simple | 0.5
Web | Service API |  | Simple | 1
Web | DB Structure |  | Simple | 0.5
Web | DB Programming |  | Simple | 0.5
Web | DB UDF |  | Simple | 0.5
Web | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Average
Web | UI Module | Custom Field Validations , Java scripting , Front end coding | Average
Web | BL | Business Logic & Validations | Average
Web | General |  | Average
Web | Service API |  | Average
Web | DB Structure |  | Average
Web | DB Programming |  | Average
Web | DB UDF |  | Average
Web | UI Design | Cosmetic Updates or Additions , Label Updates , Non Transactional Modification , New Form or Fields , Layout change | Complex
Web | UI Module | Custom Field Validations , Java scripting , Front end coding | Complex
Web | BL | Business Logic & Validations | Complex
Web | General |  | Complex
Web | Service API |  | Complex
Web | DB Structure |  | Complex
Web | DB Programming |  | Complex
Web | DB UDF |  | Complex
AI/ML Model | Data sources | Data Source Identification: Number of websites, APIs, or repositories to scrape. | Simple | 3 | 5 | 8 | 12
AI/ML Model | Extraction Method | Web scraping libraries (e.g., BeautifulSoup, Scrapy). | Simple | 3 | 5 | 8 | 12
AI/ML Model | Extraction Method | API integration (if available). | Simple | 3 | 5 | 8 | 12
AI/ML Model | Data Cleaning & Pre-processing | Removing noise, duplicates, and irrelevant data. | Simple | 3 | 5 | 8 | 12
AI/ML Model | Data Cleaning & Pre-processing | Handling different formats (JSON, CSV, XML). | Simple | 3 | 5 | 8 | 12
AI/ML Model | Compliance | Compliance: Ensuring adherence to data scraping laws (robots.txt, privacy policies). | Simple | 3 | 5 | 8 | 12
AI/ML Model | Storage | Storage: Where and how scraped data will be stored (cloud, database). | Simple | 3 | 5 | 8 | 12
AI/ML Model | Data sources | Data Source Identification: Number of websites, APIs, or repositories to scrape. | Average | 8 | 12 | 24 | 40
AI/ML Model | Extraction Method | Web scraping libraries (e.g., BeautifulSoup, Scrapy). | Average | 8 | 12 | 24 | 40
AI/ML Model | Extraction Method | API integration (if available). | Average | 8 | 12 | 24 | 40
AI/ML Model | Data Cleaning & Pre-processing | Removing noise, duplicates, and irrelevant data. | Average | 8 | 12 | 24 | 40
AI/ML Model | Data Cleaning & Pre-processing | Handling different formats (JSON, CSV, XML). | Average | 8 | 12 | 24 | 40
AI/ML Model | Compliance | Compliance: Ensuring adherence to data scraping laws (robots.txt, privacy policies). | Average | 8 | 12 | 24 | 40
AI/ML Model | Storage | Storage: Where and how scraped data will be stored (cloud, database). | Average | 8 | 12 | 24 | 40
AI/ML Model | Data sources | Data Source Identification: Number of websites, APIs, or repositories to scrape. | Complex | 24 | 32 | 48 | 64
AI/ML Model | Extraction Method | Web scraping libraries (e.g., BeautifulSoup, Scrapy). | Complex | 24 | 32 | 48 | 64
AI/ML Model | Extraction Method | API integration (if available). | Complex | 24 | 32 | 48 | 64
AI/ML Model | Data Cleaning & Pre-processing | Removing noise, duplicates, and irrelevant data. | Complex | 24 | 32 | 48 | 64
AI/ML Model | Data Cleaning & Pre-processing | Handling different formats (JSON, CSV, XML). | Complex | 24 | 32 | 48 | 64
AI/ML Model | Compliance | Compliance: Ensuring adherence to data scraping laws (robots.txt, privacy policies). | Complex | 24 | 32 | 48 | 64
AI/ML Model | Storage | Storage: Where and how scraped data will be stored (cloud, database). | Complex | 24 | 32 | 48 | 64
Note on E3: Shakti Gohil: No of features
Note on E4: Shakti Gohil: Group reference

## Estimation
Platform (Desktop / Web / Mobile) | Module | Component | Features | Make/ Reuse | Complexity (Simple / Complex / Average) | Previous Project Actual |  | Estimate Hrs. by Expert - 1 (Suhail Ahmed -1) | [8 empty] | Calculated columns | [15 empty] | Efforts |  |  | Description / Remark
[6 empty] | Project Name | Actual (working day) | UI Design | UI Module | BL | General | Service/ API | DB Struct. | DB Prog. | DB - UDF | # Comp. | Total [I - Q] | Unit Test | Func. Test | Sys. Test | Integ. Test | Reg. Test | Deployment | Req. Review | Std. Doc. | Cmmi Doc. | Code Review | Other | Total [S - AC] | Total [ R + AD ] | Total Hrs [ Make/ Reuse] | Tot. Working Days | Person - 2 | Person - 3 | Final Estimate Men Days
[18 empty] | YES | YES | YES | YES | NO | YES | YES | YES | NO | YES
[18 empty] | 10 | 8 | 4 | 4 | 4 | 2 | 10 | 3 | 10 | 2 | 20
Web | Conversational Interface | Chat UI | Chat-first interface with multi-turn, attachments, language toggle in header | Make | Complex |  |  | 12 | 20 | 20 | 13.8 | 14 | 10 | 14 | 2 | 6
Web | Conversational Interface | Use Case Selector | Dropdown/icon-based module selection and routing | Make | Simple |  |  | 3 | 5 | 4 | 1.8 | 0 | 0 | 0 | 0 | 2
Web | Prompting & Actions | Prompt Suggestions | Contextual suggestions buttons & recent query memory | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 3
Web | Prompting & Actions | Voice Input | Voice-to-text microphone capture and offline STT | Reuse | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 3
Web | Prompting & Actions | Text-to-Speech | 'Listen to Report' playback across modules (English only Phase 1) | Reuse | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 3
Web | File Handling | Upload Panel | Upload PDFs/DOCX/CSV/images with validation and progress | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 4
AI/ML | Knowledge Sync | Ingestion Service | Parse, OCR, chunk, embed, tag; update FAISS + Postgres metadata | Reuse | Complex |  |  | 0 | 0 | 20 | 9 | 14 | 10 | 14 | 2 | 0
DevOps | Knowledge Sync | Offline Sync | File-based local/intranet sync with deferred queues | Make | Average |  |  | 0 | 0 | 10 | 4.5 | 7 | 5 | 7 | 1 | 0
Web | Authentication | Sign In | Username/password sign-in with language preference in profile | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 3
Web | Authentication | Password Reset | Admin-triggered or email-based reset with token (LAN) | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 2
API | Authentication | Session Management | Secure session handling with idle timeouts and CSRF | Make | Simple |  |  | 0 | 0 | 4 | 0.6 | 0 | 0 | 0 | 0 | 0
Web | User Management | RBAC | School-based RBAC with role-specific module access | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 3
Web | User Management | Access Management | Admin UI to create/delete users, assign/revoke roles, default permissions | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 3
Web | Inspection Flow | Start New Inspection | Initiate session with framework + metadata + optional SIS fetch | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 4
Web | Inspection Flow | Upload Evidence | Upload, validate, extract, tag, link to sections | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 3
Web | Report Generation | Generate Report | Canvas view with sectioned report per framework; inline edit; narration | Make | Complex |  |  | 12 | 20 | 20 | 13.8 | 14 | 10 | 14 | 2 | 6
Web | Output Management | Reports Library | Search & filter prior reports; RBAC-based open read-only/edit | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 4
Web | Content & Planning | Lesson Plan Generator | AI-assisted lesson plan generation aligned to curriculum with editing & export | Make | Complex |  |  | 12 | 20 | 20 | 13.8 | 14 | 10 | 14 | 2 | 5
Web | Student Assistant | Assistant Core | Scoped conversational assistant with RAG to teacher-approved materials | Make | Complex |  |  | 12 | 20 | 20 | 13.8 | 14 | 10 | 14 | 2 | 5
Web | Admissions | Process Assistant | Conversational support for intake, status queries, eligibility, scheduling | Make | Average |  |  | 6 | 10 | 10 | 6.9 | 7 | 5 | 7 | 1 | 4
Web | Marketing | Campaign Generator | Generate image+caption with canvas editor via Fabric.js; brand kit enforcement | Reuse | Complex |  |  | 12 | 20 | 20 | 13.8 | 14 | 10 | 14 | 2 | 5
AI/ML | AI Orchestration | Router | Route to 4 LLMs, fallback handling, model chaining with lineage metadata | Reuse | Complex |  |  | 0 | 0 | 20 | 9 | 14 | 10 | 14 | 2 | 0
AI/ML | AI Orchestration | Retrieval | Shared retrieval with FAISS + reranker; session-scoped indexes | Reuse | Complex |  |  | 0 | 0 | 20 | 9 | 14 | 10 | 14 | 2 | 0
API | Communication & Security | API Gateway | JWT auth, RBAC enforcement, mTLS between services on LAN subnet | Make | Average |  |  | 0 | 0 | 10 | 4.5 | 7 | 5 | 7 | 1 | 0
API | Output Management | PDF Service | Server-side PDF rendering with templates and annex support | Make | Average |  |  | 0 | 0 | 10 | 4.5 | 7 | 5 | 7 | 1 | 0
Data | Database | Schema Design | PostgreSQL schema for users, roles, sessions, uploads, KB, logs, reports | Make | Complex |  |  | 0 | 0 | 20 | 9 | 14 | 10 | 14 | 2 | 0
DevOps | DevOps | Env & CI/CD | Appliance env setup, container orchestration, secrets, monitoring hooks | Make | Average |  |  | 0 | 0 | 0 | 24 | 8 | 4 | 4 | 0 | 0
Data | Logging & History | Audit Trail | Event logs for prompts, uploads, model use, downloads | Make | Average |  |  | 0 | 0 | 10 | 4.5 | 7 | 5 | 7 | 1 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
[33 empty] | 0 | 0 | 0
Note on O2: Shakti Gohil: Database proframming [ procedure / view / function ]
Note on S2: Shakti Gohil: Unit/ Func./Sys./Integ./Reg. = Total % should not be more than 30%
Note on T2: Shakti Gohil: Unit/ Func./Sys./Integ./Reg. = Total % should not be more than 30%
Note on U2: Shakti Gohil: Unit/ Func./Sys./Integ./Reg. = Total % should not be more than 30%
Note on V2: Shakti Gohil: Unit/ Func./Sys./Integ./Reg. = Total % should not be more than 30%
Note on W2: Shakti Gohil: Unit/ Func./Sys./Integ./Reg. = Total % should not be more than 30%
Note on AF2: Shakti Gohil: Total hours caluclated after considering Make/ Reuse
Note on AJ2: Shakti Gohil: Shakti Gohil: (after discussion, review with DMT/ SMT)

## WBS
[12 empty] | 0 | 0
Apollonian - AI Chatbot
Today's Date: |  |  |  | (vertical red line)
Start Date: |  | 2024-10-01 |  |  |  |  | First Day of Week (Sun=1): |  |  |  |  | 2
WBS | Tasks/Module | Resource(s) | Planned Start | Planned End | Revised Planned Start | Revised Planned End | Actual Start | Actual End | Estimation Days | % Complete | Days Complete | Days Remaining
1 | Overall Timeline
2 | Admin Portal | 6 | [6 empty] | 1
3 | User | [7 empty] | 4
4 | User Role | [7 empty] | 1
5 | User Role Permission | [7 empty] | 5
6 | User, Role - Permission mapping | [7 empty] | 5
Total development time (N Resources) | [7 empty] | Months
# | Resources | Days | No. of. Resources | Allocation
1 | AI/ML Developer | 5 | 1 | Part time
2 | UI/ Ux Designer, Developer | 5 | 1 | Part time
3 | Python - Backend Developer (Fast API, automation) | 5 | 1 | Full time
5 | Quality Assurance - QA | 5 | 1 | Part time
6 | BA - Business Analyst | 5 | 1 | Part time
7 | Technical Lead/ Project Manager | 5 | 1 | Part time
Note on M1: COMMERCIAL USE LICENSE This spreadsheet has been commercially licensed from Vertex42 LLC (the "Licensor"). If you have received this file from anyone other than the Licensor or the designated Licensee, as allowed in the commercial license agreement, please destroy all copies of this spreadsheet in your possession and report the violation to Vertex42.com. See the following page page for details about the commercial use license: http://www.vertex42.com/licensing/EULA_commercialuse.html Restrictions (a) You may not distribute, sell, rent, lease, sublicense, or otherwise transfer rights to, any portion of this Software. The Licensee may only give a copy of this spreadsheet to an individual client if the client has also purchased a commercial license of the Software. (b) You may not remove, alter, or hide the original logo, trademarks, copyright, hyperlinks, disclaimers, terms of use, or other proprietary notices. (c) You may not place the Software onto a server or computer so that it is accessible via a public network, such as the internet. (d) You may not merge the Software into another program or create any derivative works of the Software or its documentation. (e) You may not copy the Documentation or copy the Software except as indicated in the Commercial Use Grant. (f) You may not reverse engineer, decompile, or disassemble the Software. No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Somes states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.

## Summary
Effort Distribution
Phases | Efforts
Encrypt all uploads and data at rest | 1
Encrypt data in transit (HTTPS, TLS) | 1
Capture cost per request | 2
Logging / Usage tracking | 2
Master system prompt generation for story text | 1
Master system prompt generation for image styling and theme based on whole story to ensure consistency | 2
Cover image prompt generation | 2
Per-page image prompt generation | 1
Cover image generation | 2
Per-page image generation | 2
Per-page story generation based on master system prompt | 2
Language interation (English/ Arabic) | 2
Cover Page Image Generation | 2
Image generation for each page based on pre-defined template prompts | 2
Buffer (20%)
Total